## Sheet1
# | Implemented | Verified | Task | Subtask | Original Document | 180727 Draft Page | 180816 Draft Page (All Markup) | 180820 Draft Page (All Markup)
Fold in Known Issues for Ver6_1
1 | (implies change to global numbering of sections AND revision of "GENERAL RESERVED PARAMETERS" section) |  | 1 | Muranyi | page 202 | 214
2 | 180727 | 180727 | 2 | Clark | page 56 | 65
3 | 180816 | 180816 | 3 | Muranyi | page 193 | 210 | 210
4 | 180816 | 180816 | 4 | Mirmak | page 28,65[, 257] |  | 41, 78, 291
5 | 180817 | 180817 | 5 | Biernacki | page 235,236 |  | (255; see also #21 below)
6 | 180816 | 180817 | 6 | Clark | page 232,234,235,237 |  | 251, 253, 254, 256
7 | 180816 | 180817 | 7 | Clark | page 242 |  | 261
8 | 180727 | 180817 | 8 | Ross | page 4 |  | 7
9 | 180816 |  | 9 | Ross | page 72 |  | 85
10 | 180816 |  | 10 | Mirmak | page 41 |  | 54
11 | 180816 |  | 11 | Mirmak | page 180 |  | 197
12 | 180816 |  | 12 | Clark | page 78 |  | 91
13 | 180816 |  | 13 | Biernacki | leading caps after formulas |  | 198,235,236,240,243,244,245,289,292
14 | 180816 |  | 14 | Clark | page 226 |  | 244,245
15 | 180816 |  | 15 | Muranyi | page 245 |  | 264
16 | 180816 |  | 16 | LaBonte | page 172,193 |  | 189, 210
17 | 180816 |  | 17 | Muranyi | page 126 |  | 131
18 | 180816 |  | 18 | Muranyi | page 142 (should be 143 in PDF) |  | 158
19 | 180816 |  | 19 | Muranyi | page 104 |  | 117
20 | 180816 |  | 20 | Mirmak | page 172,193 |  | 189
21 | withdrawn |  | 21 | Ross | page 235,236 |  | 255
22 | 180816 |  | 22 | Muranyi | page 110,123 |  | 123, 138
23 | 180816 |  | 23 | Ross | page 193 |  | 210
Fold in BIRDs (try from back to front to preserve earlier page number references such as working on the IBIS-AMI changes first and then the earlier sections.
24 | 180816 |  | 1 | BIRD147.6 Back-channel Support |  |  | 266-274
25 | 180816 |  | 2 | BIRD158.7 AMI Touchstone (R) Analog Buffer Models (Superseded by BIRD194 below) |  |  | 275-279
26 | 180816 |  | 3 | BIRD165.1 Parameter Passing Improvements for [External Circuit] Package Models with [Circuit Call] |  |  | 144
27 | 180816 |  | 4 | BIRD179 New IBIS-AMI Reserved Parameter Special_Param_Names |  |  | 225-227
28 | 180816 |  | 5 | BIRD180 Require Unique Pin_Names in [Pin] |  |  | 26
29 | 180816 |  | 6 | BIRD182 POWER and GND [Pin] signal_name as [Pin Mapping] bus_label |  |  | 34-35
30 | 180816 |  | 7 | BIRD183 [Model Data] Matrix Subparameter Terminology Correction |  |  | 20,21,162
31 | 180816 |  | 8 | BIRD184.2 Model_name and Signal_name Restriction for POWER and GND Pins |  |  | 26
32 | 180816 |  | 9 | BIRD185.2 Section 3 Reserved Word Guideline Update |  |  | 13-14
33 | 180816 |  | 10 | BIRD186.4 File Naming Rules |  |  | 15, 23, 106, 113-114, 133-136, 139-142
34 | 180816 |  | 11 | BIRD187.3 Format and Usage Out Clarifications |  |  | 213-214, 218
35 | 180816 |  | 12 | BIRD188.1 Expanded Rx_Noise Support for AMI |  |  | 246-249
36 | 180816 |  | 13 | BIRD189.7 Interconnect Modeling Using IBIS-ISS and Touchstone |  |  | 25, 28-34, 37-38, 154, 294-327
37 | 180816 |  | 14 | BIRD191.2 Clarifying Locations for Si_Location and Timing_Location |  |  | 25
38 | 180816 |  | 15 | BIRD192.1 Clarification of List Default Rules |  |  | 213
39 | 180816 |  | 16 | BIRD193 Figure 29 Corrections |  |  | 145-149
40 | 180816 |  | 17 | BIRD194 Revised AMI Ts4file Analog Buffer Models |  |  | 275-279
41
Fold in Known Issues for BIRDs in Ver7_0_wip
42 | 180727 |  | 1 | Wolff | page 28 | 305
43 | 180820 |  | 2 | Biernacki | connection to "Touchstone files" |  |  | 28, 301, 306
44 | 180820 |  | 3 | Butterfield | page 41 |  |  | 318
45 | 180820 |  | 4 | Ross | page 24 |  |  | 301
46 | 180820 |  | 5 | Ross | page 26 |  |  | 303
| 180820 |  | 6 | Ross | page 6 |  |  | 279
Create two new sections or chapters for BCI and Interconnect Models
47 | 180727 |  | 1 | BCI section |  | 266ff
48 | 180727 |  | 2 | Interconnect section |  | 294ff
General Finalization
49 |  |  | 1 | Update the AMI section tables with all new IBIS-AMI parameters
50 |  |  | 2 | Update Section 10.8 with the new AMI parameters
51 |  |  | 3 | Update Table and Figure Caption numbers/references as needed due to new information
52 | 180727 |  | 4 | Update Section 3.1 Tree by deleting some subparameters per BIRD183 |  | 20, 21
53 | 180727 |  | 5 | Add to Section 2.0 – the new BIRDs for V7.0 and number of BIRDs |  | 11, 12
54 |  |  | 6 | Update Versions 6.1 -> 7.0, Full dates first, then years only 2015 -> 2018 and Copyright years, all embedded throughout the document.
55 |  |  | 7 | Issue new correction BIRD(s), if needed identified as a result of the editorial pass and include them
56 |  |  | 8 | Update capitalization of sections and cross-references to sections
57 |  |  | 9 | Update Table of Contents (paying attention to capitalization)