## Slide 1: Revisiting the IBIS Version Release Schedule
Michael Mirmak
Chair, IBIS Open Forum
European IBIS Summit
Ghent, Belgium
May 14, 2014
Presented by Randy Wolff, Micron Technology

## Slide 2: Review Previous Proposal for IBIS Development – Feb. 2012

## Slide 3: Release Schedule for IBIS
Moving to a regular, software-like release plan
  Allows better planning by “customers” (IBIS community)
  Keeps number of changes manageable
  Reduces & stabilizes parser development cycle time and cost
Two “cycles”, each with two parts
  Cycle 1
    Nov. – Feb.: technical development
    March 1 – close technical changes
    May 1 – close final document (editorial fixes in-between)
  Cycle 2
    May – Aug.: technical development
    Sept. 1 – close technical changes
    Nov. 1 – close final document (editorial fixes in-between)
From
Feb. 2012

## Slide 4: How Does This Work?
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
BIRD Development
BIRD Development
BIRD Development
Cycle 1
Cycle 2
Editorial
Work
Editorial
Work
Parser development can start as early as this point
Document votes & releases here
From
Feb. 2012

## Slide 5: Revised proposal

## Slide 6: Release Schedule for IBIS
Need to move to 9+ month cycle
  Feedback from 2014 DesignCon IBIS Summit
New proposal: annual cycle with three parts
  Technical Period
    February - July
    August 1 - close technical changes
  Editorial Period
    August - September
    Nov. 1 - close & vote on final document
  Quiet Period (Events, Holidays)
    November - January

## Slide 7: How Does This Work?
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
BIRD Development
for a Given Version
Events & Holidays
Technical Development
Editing
Editorial
Work
Parser development can start as early as this point
Document vote & release here
Events & Holidays

## Slide 8: Why This Schedule?
Calendar can limit potential interactions
  End-of-year holidays/shutdowns
  Fall Asian IBIS Summits and preparation
  New Year celebrations in Asia
  DesignCon Summit and preparation
  July/August vacation schedule in Europe
Member companies are likely affected by the same calendar items
  Peak work periods are Sept. - Oct. and March - May

## Slide 9: IBIS Numbering Proposal
Specification moves to date codes
  Year and month of approval (e.g., 2014.11)
  Multiple releases in the same month unlikely
  Major/minor release distinction goes away
  [IBIS Ver] and AMI_Version affected
Parser versions track specifications
  Parser uses specification release number, for features
  Parser updates use additional numbers
    e.g.,2014.11 r01 or similar
  Name changes to simply “ibischk”

## Slide 10: Implications
If implemented immediately…
  Next version is not 6.x or 7, but 2014.11
  BIRDs for 2014.11 must be approved on/before Aug. 1, 2014
Membership dues in 2015
  Parser development fees become part of membership dues
Is this schedule realistic for the IBIS community?
Can tools and design cycles absorb annual updates?

## Slide 11: Q/A